## Procurement Status
BUSH LEGACY BUILDERS
Sierant Residence — Procurement Selection Status Update
Prepared: April 06, 2026 ¦ 406 Cedar Street Suite 101, Sandpoint ID 83864 ¦ 208.290.2186
LEGEND: | Overdue | Need Sign-off | Pending | Approved | Not Started
Category | Selection Item | Selection Deadline | Approval Status | Install Deadline | Budget Allowance | Notes
Preconstruction
| Windows and Exterior Doors | 2026-01-01 | Approved | 2026-04-06 | 413647.06
| Timber Truss System | 2026-01-01 | Approved | 2026-03-01 | 150000
Architectural Exterior Drivers
| Exterior paint & stain colors | 2026-02-01 | Need Sign-off | 2026-04-06 |  | Need new sample approval
| Roofing material & color | 2026-02-01 | Approved | 2026-04-06 | 135570.59
| Exterior Fascia | 2026-02-01 | Approved | 2026-04-06 | 20000
| Exterior siding material wood | 2026-02-01 | Approved | 2026-04-06 | 105000
| Exterior soffit material | 2026-02-01 | Approved | 2026-04-06 | 50000
| Masonry | 2026-02-01 | Approved | 2026-04-06 | 238648
Architectural Interior Drivers
| Integration Scope & Layout | 2026-03-01 | Overdue | 2026-06-08 | 224117.65
| Fireplace | 2026-03-01 | Overdue | 2026-04-06 | 32941.18 | Need to meet with Casey ASAP
| Fireplace Surround (hearth & mantel) | 2026-03-01 | Overdue | 2026-04-06 | 5429.86
| HVAC equipment type | 2026-03-01 | Pending | 2026-04-15
| Electrical Layout | 2026-03-01 | Pending | 2026-05-14
| Under cabinet lighting | 2026-03-01 | Pending | 2026-09-04
| Front entry door | 2026-03-01 | Pending | 2026-09-04 | 10000
| Front entry door hardware | 2026-03-01 | Pending | 2026-10-05 | 1000
| Appliances | 2026-03-01 | Approved | 2026-12-21 | 129411.76
| Plumbing Fixtures | 2026-03-01 | Approved | 2026-10-09 | 78523.53
| Lighting Fixtures | 2026-03-01 | Approved | 2026-12-21 | 52941.18
| Exterior lighting fixtures | 2026-03-01 | Approved | 2026-12-21
| Thermostat system | 2026-03-01 | Not Started | 2026-04-15
| Vent hood design | 2026-03-01 | Not Started | 2026-09-04
| Gutters | 2026-03-01 | Not Started | 2026-06-29 | 10000
| Outdoor ceiling fans | 2026-03-01 | Not Started | 2026-12-21
| Outdoor heaters | 2026-03-01 | Not Started | 2026-12-21
Interior Design Drivers
| Cabinets | 2026-04-01 | Pending | 2026-09-04 | 204117.65 | John updating Shops based on Lynn's comments
| Interior doors | 2026-04-01 | Pending | 2026-09-04 | 50000
| Garage Doors | 2026-04-01 | Pending | 2026-10-05 | 32352.94
| Interior door hardware | 2026-04-01 | Pending | 2026-10-05 | 8414.12
| Interior T&G | 2026-04-01 | Approved | 2026-09-04 | 40000
| Built-in | 2026-04-01 | Not Started | 2026-09-04
| Closets | 2026-04-01 | Not Started | 2026-09-04
| Cabinet hardware | 2026-04-01 | Not Started | 2026-10-05 | 3500
Hardware & Decorative Components
| Flooring | 2026-05-01 | Overdue | 2026-11-23 | 59195.29
| Tile & Layout | 2026-05-01 | Overdue | 2026-09-04 | 61176.47
| Countertops | 2026-05-01 | Pending | 2026-10-09 | 87500
| Window casing | 2026-05-01 | Pending | 2026-09-04 | 6000
| Interior Door casing | 2026-05-01 | Pending | 2026-09-04 | 7503.53
| Baseboard style | 2026-05-01 | Pending | 2026-09-04 | 9000
| Deck railing system | 2026-05-01 | Not Started | 2026-06-29
| Deck material | 2026-05-01 | Not Started | 2026-06-29 | 12764.71
| Drywall finish/texture | 2026-05-01 | Not Started | 2026-07-07
| Hardwood flooring species | 2026-05-01 | Not Started | 2026-11-23
| Hardwood plank width | 2026-05-01 | Not Started | 2026-11-23
| Hardwood stain color | 2026-05-01 | Not Started | 2026-11-23
| Carpet/Rubber selection | 2026-05-01 | Not Started | 2026-11-23
| Decorative Metal & Shelving | 2026-05-01 | Not Started | 2026-09-04
| TV Mounts | 2026-05-01 | Not Started
Final Style Integration
| Interior wall paint colors | 2026-06-01 | Not Started | 2026-08-07
| Interior Ceiling paint colors | 2026-06-01 | Not Started | 2026-08-07
| Accent wall paint | 2026-06-01 | Not Started | 2026-08-07
| Shower glass enclosure | 2026-06-01 | Not Started | 2026-11-09 | 8000
| Bath Accessories | 2026-06-01 | Not Started | 2026-11-09 | 1500
| Mirrors | 2026-06-01 | Not Started | 2026-11-09 | 1411.76
| Driveway material | 2026-06-01 | Not Started | 2026-09-07
| Walkway material | 2026-06-01 | Not Started | 2026-09-07
| Landscaping design | 2026-06-01 | Not Started | 2026-09-07
| Hot Tub | 2026-06-01 | Not Started | 2026-09-07
| Fire pit design | 2026-06-01 | Not Started | 2026-09-07
| Outdoor kitchen finishes | 2026-06-01 | Not Started | 2026-09-07
| Outdoor fireplace design | 2026-06-01 | Not Started | 2026-09-07
SUMMARY
Total Selections | 62
Approved | 12
Need Sign-off | 1
Overdue | 5
Pending | 13
Not Started | 31