## Procurement Selections
BUSH LEGACY BUILDERS
Beeksma Residence — Procurement Selection Status Update
Prepared: April 06, 2026 ¦ 406 Cedar Street Suite 101, Sandpoint ID 83864 ¦ 208.290.2186
LEGEND: | Overdue | Need Sign-off | Pending | Approved | Not Started
Category | Selection Item | Selection Deadline | Approval Status | Install Deadline | Budget Allowance
Preconstruction
| Windows and Exterior Doors | 2026-01-01 | Approved | 2026-03-02 | 64826
Architectural Exterior Drivers
| Roofing material & color | 2026-02-01 | Approved | 2026-03-16 | 72701.32
| Exterior Fascia | 2026-02-01 | Approved | 2026-05-04 | 2400
| Exterior siding material wood | 2026-02-01 | Need Sign-off | 2026-05-04 | 24948
| Exterior soffit material | 2026-02-01 | Need Sign-off | 2026-05-04 | 14725
| Masonry | 2026-02-01 | Need Sign-off | 2026-05-04 | 21000
| Exterior paint & stain colors | 2026-02-01 | Need Sign-off | 2026-05-04
Architectural Interior Drivers
| HVAC equipment type | 2026-03-01 | Approved | 2026-02-16
| Thermostat system | 2026-03-01 | Approved | 2026-02-16
| Electrical Layout | 2026-03-01 | Approved | 2026-03-09
| Integration Scope & Layout | 2026-03-01 | Approved | 2026-03-09
| Appliances | 2026-03-01 | Approved | 2026-10-05 | 16620
| Plumbing Fixtures | 2026-03-01 | Approved | 2026-06-29 | 18798
| Fireplace | 2026-03-01 | Approved | 2026-04-06 | 23305
| Garbage disposal | 2026-03-01 | Approved | 2026-06-29
| Under cabinet lighting | 2026-03-01 | Approved | 2026-06-15
| Fireplace Surround (hearth & mantel) | 2026-03-01 | Need Sign-off | 2026-04-06 | 3500
| Front entry door | 2026-03-01 | Pending | 2026-06-22 | 3750
| Vent hood design | 2026-03-01 | Pending | 2026-06-15
| Lighting Fixtures | 2026-03-01 | Pending | 2026-08-17 | 14500
| Exterior lighting fixtures | 2026-03-01 | Pending | 2026-08-17
| Gutters | 2026-03-01 | Not Started | 2026-06-22 | 4500
| Front entry door hardware | 2026-03-01 | Not Started | 2026-07-13
Interior Design Drivers
| Cabinets | 2026-04-01 | Approved | 2026-06-15 | 103231
| Interior T&G | 2026-04-01 | Approved | 2026-06-22 | 5842.5
| Interior doors | 2026-04-01 | Need Sign-off | 2026-06-22 | 20400
| Garage Doors | 2026-04-01 | Need Sign-off | 2026-06-22 | 9300
| Built-in | 2026-04-01 | Not Started | 2026-06-15
| Closets | 2026-04-01 | Not Started | 2026-06-15
| Cabinet hardware | 2026-04-01 | Not Started | 2026-06-22 | 2200
| Interior door hardware | 2026-04-01 | Not Started | 2026-07-13 | 2688
Hardware & Decorative Components
| Deck railing system | 2026-05-01 | Approved | 2026-08-17 | 11520
| Deck material | 2026-05-01 | Approved | 2026-08-17 | 11050
| Flooring | 2026-05-01 | Need Sign-off | 2026-07-20 | 28224
| Drywall finish/texture | 2026-05-01 | Need Sign-off | 2026-04-20
| Tile & Layout | 2026-05-01 | Overdue | 2026-06-08 | 48000
| Countertops | 2026-05-01 | Overdue | 2026-06-29 | 32656
| Hardwood flooring species | 2026-05-01 | Pending | 2026-07-20
| Hardwood plank width | 2026-05-01 | Pending | 2026-07-20
| Hardwood stain color | 2026-05-01 | Pending | 2026-07-20
| Carpet/Rubber selection | 2026-05-01 | Pending | 2026-07-20 | 15281.5
| Window casing | 2026-05-01 | Not Started | 2026-06-22 | 6000
| Interior Door casing | 2026-05-01 | Not Started | 2026-06-22 | 8315
| Baseboard style | 2026-05-01 | Not Started | 2026-06-22 | 9000
| TV Mounts | 2026-05-01 | Not Started | 2026-06-22 | 650
Final Style Integration
| Interior wall paint colors | 2026-06-01 | Overdue | 2026-05-18
| Interior Ceiling paint colors | 2026-06-01 | Overdue | 2026-05-18
| Accent wall paint | 2026-06-01 | Overdue | 2026-05-18
| Shower glass enclosure | 2026-06-01 | Not Started | 2026-10-05 | 6000
| Bath Accessories | 2026-06-01 | Not Started | 2026-10-05 | 1500
| Mirrors | 2026-06-01 | Not Started | 2026-10-05 | 1200
| Driveway material | 2026-06-01 | Not Started | 2026-08-17
| Walkway material | 2026-06-01 | Not Started | 2026-08-17
| Landscaping design | 2026-06-01 | Not Started | 2026-08-17
| Hot Tub | 2026-06-01 | Not Started | 2026-08-17
| Fire pit design | 2026-06-01 | Not Started | 2026-08-17
| Outdoor kitchen finishes | 2026-06-01 | Not Started | 2026-08-17
SUMMARY
Total Selections | 57
Approved | 16
Need Sign-off | 9
Overdue | 5
Pending | 8
Not Started | 19